## Minteng Xie
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 11 | 9 | 2 | 0 - learning python, git 1 - research other PM tools, write "Idea Sharing" 5 - group meetings 6 - review and research security process | 5 | 2 |  |  |  | 2 | 2 | 0 - learning python, git 1 - decide the added features, write "Idea Sharing" 5 - group meetings 6 - research more about security process | 12
week 2 (02/03 - 02/09) | 12 | 9 | 3 | 0 - learning python, git, installation 1 - research other PM tools, write "Idea Sharing" 5 - group meetings, online meeting 6 - review and research security process, write SPPP | 6 | 1 |  |  |  | 3 | 2 | 0 - learning python, git, 1 - using pivot tracker 3 - fix bugs 4 - test exising code and softwate 5 - group meetings 6 - research more about security process | 12
week 3 (02/10 - 02/16) | 11 | 9 | 2 | 0 - learning python, git, installation, django 1 - wirte in pivotaltracker 5 - group meetings 6 - read the existing code and documentation | 5 | 1 |  |  |  | 2 | 3 | 0 - learning python, git, django 1 - using pivotaltracker 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 12
week 4 (02/17 - 02/23) | 11 | 9 | 2 | 0 - learning python, django 1 - write in pivotaltracker 4 - design selenium test on test_authentication 5 - group meetings 6 - read the existing code and documentation | 4 | 1 |  |  | 2 | 2 | 2 | 0 - learning python, django 1 - using pivotaltracker 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 12
week 5 (02/24 - 03/01) | 11 | 9 | 2 | 0 - learning python, django 1 - write in pivotaltracker 4 - design new selenium test, test report 5 - group meetings 6 - read the existing code and documentation | 2 | 1 |  |  | 4 | 2 | 2 | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 12
week 8 (03/16 - 03/22) | 14 | 12 | 2 | 0 - learning django 2 - design new feature "no duplicate project title" 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code, draw the use case diagram and wirte use case description | 3 |  | 1 | 4 | 1 | 2 | 3 | 0 - learning django 2 - design new feature "no duplicate project title" 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code and documentation | 12
week 9 (03/23 - 03/29) | 11 | 9 | 2 | 0 - learning django 2 - design new features: duplicate project title, sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code, prepare for the presentation | 2 |  | 2 | 2 | 2 | 2 | 1 | 0 - learning django 2 - design new feature 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code and documentation | 12
week 10 (03/30 - 04/05) | 8 | 8 | 0 | 0 - learning django 2 - design new features: sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code | 2 |  | 3 | 1 | 1 |  | 1 | 0 - learning django 2 - design new feature 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code and documentation | 12
week 11 (04/06 - 04/12) | 10 | 8 | 2 | 0 - learning django 2 - design new features: sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code | 2 |  | 2 | 2 | 1 | 2 | 1 | 0 - learning django 2 - design new feature 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code and documentation | 12
week 12 (04/13 - 04/19) | 10 | 10 | 0 | 2 - design new features: sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin |  |  | 2 | 4 | 2 |  | 2 | 2 - design new features: sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin | 12
week 13 (04/20 - 04/27) | 14 | 10 | 2 | 2 - design new features: sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin, write SPPP,SDD |  |  | 2 | 2 | 2 | 2 | 6

## Nora Salamah
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 12 | 10 | 2 | 0 - learning python, git, clone project. 1 - research other management tools - come up with new features, and requirements. 5 - Group meetings 6 - Work on current 3blueprint site and figure fixes and bugs | 6 | 2 |  |  |  | 2 | 2 | 0 - learning python, git. 1 - research other management tools - gather requirements & features. 5 - Group meetings | 12
week 2 (02/03 - 02/09) | 13 | 9 | 3 | 0 - learning python, git. 5 - Group meeting, Online meeting. 6 - Work on my parts of SPPP report. - Work on presentation. - Write user stories (Pivotol) - Create presentation & prepare for it. | 3 |  |  |  |  | 3 | 6 | 0 - learning python, git, django/installing django. 5 - Group meetings | 12
week 3 (02/10 - 02/16) | 10 | 8 | 2 | 0 - learning python, git. 1 - Write user stories (Pivotol) 5 - Group meetings. 6 - installing Vmware. - Studying existing system & documentations. | 4 | 1 |  |  |  | 2 | 3 | 0 - learning python, git, django. 5 - Group meetings | 10
week 4 (02/17 - 02/23) | 11 | 9 | 2 | 0 - learning python, selenium. 1 - Write user stories (Pivotol tracker) 4 - Understandig & testing existing selenium tests. 5 - Group meetings. 6 - update SPPP report (requirements part as professor's comments) | 4 | 1 |  |  | 3 | 2 | 1 | 0 - learning python, git, django. 5 - Group meetings | 1
week 5 (02/24 - 03/30) | 14 | 12 | 2 | 0 - learning python, selenium. 4 - Test existing selenium tests. - Create new selenium tests. 5 - Group meetings. 6 - update SPPP report (for 1st iteration) - Fill post iteration form - Fill test report | 4 |  |  |  | 4 | 2 | 4 | 0 - learning python, git, django. 5 - Group meetings | 14
week 8 (03/14 - 03/22) | 12 | 10 | 2 | 0 - learning git, django 3 - Fix existing bugs in current system (itertion start & end date constraints) (user story hours > 0) 5 - Group meetings. 6 - create own branch and clone project to it. | 4 |  |  | 4 |  | 2 | 2 |  | 12
week 9 (03/23 - 03/30) | 16 | 10 | 4 | 0 - learning git, python 3 - Fix existing bugs in current system (itertion start & end date constraints) (user story hours > 0) - Create test for new codes. 5 - Group meetings. 6 - clone project and work on me & Zhi's branch and merges our changes with team | 3 |  |  | 5 |  | 4 | 4 |  | 16
week 10 (03/31 - 04/06) | 7 | 5 | 2 | 0 - learning git, python 5 - Group meetings. 6 - Comeup with new ideas for itertion 3 | 3 |  |  |  |  | 2 | 2
week 11 (04/07 - 04/13) | 9 | 7 | 2 | 0 - learning git, django 5 - Group meetings. 6 - Work on new features for itertion 3 | 3 |  |  |  |  | 2 | 4
week 12 (04/14 - 04/20) | 10 | 7 | 2 | 0 - learning git, django 5 - Group meetings. 6 - Work on new features for itertion 3 | 3 |  |  |  |  | 2 | 5
week 13 (04/21 - 04/27) | 19 | 14 | 5 | 0 - learning git, django 3- Work on new features for itertion 3 (timeout handler, role dropdown, logot when page closed) 5 - Group meetings. 6 - clone project and work on me & Zhi's branch and merges our changes with team - Create final presentation - update SPP, testing doc, pivotal tracker | 3 |  |  | 5 |  | 6 | 5

## Zhi Dou
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 8 | 6 | 2 |  | 3 | 3 | 0 | 0 | 0 | 2 | 0 | sppp and learn python | 5
week 2 (02/03 - 02/09) | 5 | 3 | 2 |  | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 - learning python, git, 1 - using pivot tracker 3 - fix bugs 4 - test exising code and softwate 5 - group meetings 6 - research more about security process | 8
week 2 (02/03 - 02/09) | 8 | 6 | 2 | 0 - learning python, git, installation 1 - research other PM tools, write "Idea Sharing" 5 - group meetings, online meeting 6 - review and research security process, write SPPP | 6 | 1 |  |  |  | 1 |  | 0 - learning python, git, 1 - using pivot tracker 3 - fix bugs 4 - test exising code and softwate 5 - group meetings 6 - research more about security process | 8
week 3 (02/10 - 02/16) | 8 | 6 | 2 | 0 - learning python, git, installation, django 1 - wirte in pivotaltracker 5 - group meetings 6 - read the existing code and documentation | 5 | 1 |  |  |  | 2 |  | 0 - learning python, git, django 1 - using pivotaltracker 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 8
week 4 (02/17 - 02/23) | 10 | 8 | 2 | 0 - learning python, django 1 - write in pivotaltracker 4 - design selenium test on test_authentication 5 - group meetings 6 - read the existing code and documentation | 4 | 0.5 |  |  | 2.5 | 1.5 | 2.5 | 0 - learning python, django 1 - using pivotaltracker 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 8
week 5 (02/24 - 03/01) | 8 | 6 | 2 | 0 - learning python, django 1 - write in pivotaltracker 4 - design new selenium test, test report 5 - group meetings 6 - read the existing code and documentation | 2 |  |  |  | 5 | 1 |  | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 12
week 6 (03/02 - 03/08) | 6 | 4 | 2 | 0 - learning python, django 1 - write in pivotaltracker 4 - design new selenium test, test report 5 - group meetings 6 - read the existing code and documentation | 3 |  |  |  |  | 2 | 1 | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 10
week 7 (03/09 - 03/15) | 6 | 4 | 2 | 0 - learning python, django 1 - write in pivotaltracker 4 - design new selenium test, test report 5 - group meetings 6 - read the existing code and documentation | 4 |  |  |  |  | 2 | 0 | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 10
week 7 (03/016 - 03/22) | 20 | 17 | 3 | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | 11 |  | 2 | 4 |  | 3 | 0 | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 20
week 7 (03/22 - 03/29) | 25 | 22 | 3 | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | 2 |  | 4 | 8 | 8 | 3 | 0 | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 20
week 7 (03/30 - 04/05) | 10 | 9 | 1 | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | 7 |  | 0 | 0 | 0 | 3 | 0 | 0 - learning python, django 1 - requirement analysis 2 - design new features 4 - test exising code and softwate 5 - group meetings 6 - read existing code and docementation | 20

## Rui Dai
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 10 | 8 | 2 | 0 - start learning python & git environment. Installation 1 - use ActiveCollab and compare it with existing management tool. List the feature and have a brian storm during the meeting. 5 - Create Slack team. Host the first meeting. Clone the 3blueprint from git. | 3 | 1 |  |  |  | 4 |  | 0 - learning python, git. 1 - research other management tools - analysis features and how to write requirement paper. 5 - Group meetings
week 2 (02/3 - 02/10) | 12 | 9 | 3 | 0 - learning python & git 1 - use Pivot Tracker and write User Story in icebox 3 - complete the SPPP document 5 - slack meeting on Monday and extra meeting on Wednesday 6 - prepare for the presentation | 3 | 3 |  |  | 2 | 3 | 1 | 0 - learning python, git. 1 - set the environment and start understand the code of the existing system. 3- design for the test 5 - Group meetings
week 3 (02/11 - 02/17) | 11 | 9 | 2 | 0 - learning python & django model and django test 1 - list the existing features 5 - holding meeting 6 - install vmware and set all the enviornment | 5 | 2 |  |  |  | 2 | 2 | 0 - learning django and test and learn how to transfer SQLite to MySQL 3 - design a test for some features 5 - group meeting | 13
week 4 (02/18 - 02/23) | 10 | 9 | 1 | 0 - learning django and test 3 - fix bugs on selenium test and write test 5 - hold meeting | 4 | 5 |  |  |  | 1 |  | 0 - learning django and test 3- write test 5 - hold meeting | 13
week 5 (02/23 - 03/01) | 11 | 9 | 2 | 0 - learning test 1 - find missing function through test 3 - write test 5 - hold meeting 6 - write test report and SPPP | 3 | 1 |  | 4 |  | 2 | 2 | 0- learning django 3 - improve the current function | 13
week 6 (03/02 - 03/09) | 6 | 6 | 0 | 0-learning django 1-analysis function for interation I 2-try to write some simple django code | 3 | 1 | 2 |  |  |  |  | 0-learning django 1-analysis what to do in the iteration II 2-design for the code 3-write code | 15
week 7 (03/10 - 03/16) | 17 | 15 | 2 | 0-learning django and the code about create project 1- write user case 3- wirte code about no duplicate project name 4-write test 5-hold meeting | 3 | 2 |  | 9 | 1 | 2 |  | 0-learning django 1-start to working on a new feature 2-design for the code 3-write code | 18
week 8 (03/17 - 03/23) | 17 | 12 | 5 | 0 -learning djange and the code about duplicate name and get IP address 3 - write code about duplicate project name and IP address 4 - write the test for these two user story 5- take meeting | 3 |  |  | 5 | 4 | 5 |  | 0-learning django 1-start to working on security 2-design for the code 3-write code | 18
week 9 (03/24 - 03/30) | 15 | 11 | 4 | 0 -learning djange and the code about store IP address and compute time 2- decide to pause 60 sec for next try 3 - write code about IP address and compute time 5- take meeting 6 - prepare for presentation | 5 |  | 1 | 5 |  | 4 |  | 0-learning django 1-accomplish pause time 2-design for the code 3-write code | 20
week 10 (03/31 - 04/06) | 15 | 11 | 4 | 0 -learning about django security 3 - write code about lock users and debug 5- take meeting | 3 |  | 4 | 4 |  | 4 |  | 0-learning django 1-accomplish the function of lock users 3-write code | 20
week 11 (04/7 - 04/13) | 15 | 11 | 4 | 0 - learning about django defender 2 - try to install django defender and make it work 3 - have problem usering django defneder and decide not to use it 5 - take meeing | 3 |  | 3 | 5 |  | 4 |  | 0-learning django 1-accomplish the function of lock users 3-write code 4 - write test 6 - check the team work and help to merge | 20
week 12 (04/14 - 04/20) | 24 | 20 | 4 | 0 -learning about creating django model 1 - analyize the requirement for lock account 2 - design (decide to create new model to stora IP address and login time) 3 - write code to implenment 4 - testing the new feature 5- take meeting | 2 | 1 | 1 | 10 | 3 | 4 |  | 1 - analyize the requirement and write the SPPP file 4 - test whole project 5 - take meeting 6 - check the team work, prepare for the presentation | 15
week 13 (04/21 - 04/27) | 15 | 10 | 5 | 1 - analyize the requirement and write the SPPP file 4 - test whole project 5 - take meeting 6 - check the team work, prepare for the presentation

## Divyam Hansaria
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 12 | 10 | 2 | 0 - learning python, git, clone project. 1 - research other management tools 5 - Group meetings 6 - Work on current 3blueprint site and figure fixes and bugs | 4 | 1 |  |  |  | 2 | 3 | 0 - learning python, git. 1 - research other management tools 5 - Group meetings 6 - Work on current site and figure out fixes. | 12
week 2 (02/03 - 02/09) | 10 | 8 | 2 | 0 - learning python 1- reseach on management tools 5 - group meetings, online meeting 6 - search about coding standards, tools, configuration management | 2 | 2 |  |  |  | 2 | 2 | 0 - learning python, git, 1 - using pivot tracker 3 - fix bugs 4 - test exising code and softwate 5 - group meetings 6 - research more about security process | 10
week 3 (02/10 - 02/16) | 10 | 8 | 2 | 0 - learning python 1- reseach on management tools 5 - group meetings, online meeting 6 - search about coding standards, tools, configuration management | 2 | 2 |  |  |  | 2 | 2 | 0 - learning python, git, 4 - test exising code and softwate 5 - group meetings | 20
week 4 (02/17 - 02/23) | 20 | 18 | 2 | 0 - learning python 1- reseach on management tools 5 - group meetings, online meeting 6 - search about coding standards, tools, configuration management | 2 | 2 |  |  |  | 2 | 2 | 0 - learning python,web appliction 4 - test exising code and softwate 5 - group meetings | 10
week 5 (02/24 - 03/01) | 14 | 12 | 2 | 0 - learning python, selenium. 4 - Test existing selenium tests. - Create new selenium tests. 5 - Group meetings. 6 - update SPPP report (for 1st iteration) - Fill post iteration form - Fill test report | 4 |  |  |  | 4 | 2 | 4 | 0 - learning python, git, django. 5 - Group meetings | 14
week 6 (03/02 - 03/08) | 6 | 6 | 0 | 0-learning django 1-analysis function for interation I 2-try to write some simple django code | 3 | 1 | 2 |  |  |  |  | 0-learning django 1-analysis what to do in the iteration II 2-design for the code 3-write code | 15
week 7 (03/09 - 03/15) | 17 | 15 | 2 | 0-learning django and the code about create project 1- write user case 3- wirte code about no duplicate project name 4-write test 5-hold meeting | 3 | 2 |  | 9 | 1 | 2 |  | 0-learning django 1-start to working on a new feature 2-design for the code 3-write code | 12
week 8 (03/16 - 03/22) | 12 | 10 | 2 | 0 - learning git, django 3 - Fix existing bugs in current system (Moving stories to iterations) (when no iteration excits ) 5 - Group meetings. 6 - create own branch and clone project to it. | 4 |  |  | 4 |  | 2 | 2 | 0 - learning git, django 3 - Fix existing bugs in current system - Create test for new codes. 5 - Group meetings. 6 - clone project and merges our changes with team | 16
week 9 (03/23 - 03/30) | 16 | 12 | 4 | 0 - learning git, django 3 - Fix existing bugs in current system - Create test for new codes. 5 - Group meetings. 6 - clone project and merges our changes with team | 3 |  |  | 5 |  | 4 | 4 | 0 - learning git, python 5 - Group meetings. 6 - Comeup with new ideas for itertion 3 | 16
week 10 (03/31 - 04/06) | 7 | 5 | 2 | 0 - learning git, python 5 - Group meetings. 6 - Comeup with new ideas for itertion 3 | 3 |  |  |  |  | 2 | 2 | 0 - learning git, django 5 - Group meetings. 3 - Fixs bugs in the source code 6 - Fixs bugs in the testing code | 18
week 11 (04/07 - 04/13) | 18 | 16 | 2 | 0 - learning git, django 5 - Group meetings. 3 - Fixs bugs in the source code 6 - Fixs bugs in the testing code | 3 |  |  | 7 |  | 2 | 6 | 0 - learning selenium, django 5 - Group meetings. 6 - Work on new features for itertion 3 3 - Fixs bugs in the UI Tests and write new Tests | 18
week 12 (04/14 - 04/20) | 20 | 18 | 2 | 0 - learning selenium, django 5 - Group meetings. 6 - Work on new features for itertion 3 3 - Fixs bugs in the UI Tests and write new Tests | 3 |  |  | 8 |  | 2 | 6 | 0 - learning selenium, django 3- Work on new features for itertion 3 5 - Group meetings. 6 - merge the final project and check files - Create final presentation - update SPP, testing doc, pivotal tracker | 20
week 13 (04/21 - 04/27) | 19 | 14 | 5 | 0 - learning selenium, django 3- Work on new features for itertion 3 5 - Group meetings. 6 - merge the final project and check files - Create final presentation - update SPP, testing doc, pivotal tracker | 3 |  |  | 5 |  | 6 | 5

## Abhyudaya Alva
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 10 | 8 | 2 | 0 - learning python, git 1 - research other PM tools, write "Idea Sharing" 5 - group meetings 6 - review and research security process | 4 | 2 |  |  |  | 2 | 2 | 0 - learning python, git 1 - decide the added features, write "Idea Sharing" 5 - group meetings 6 - research more about security process | 12
week 2 (02/03 - 02/09 | 8 | 6 | 2 | 0 - learning python 5 - group meetings, online meeting 6 - search about coding standards, tools, configuration management | 2 |  |  |  |  | 2 | 2 | 0 - learning python, git, 1 - using pivot tracker 3 - fix bugs 4 - test exising code and softwate 5 - group meetings
week 3 (02/10 - 02/016 | 8 | 6 | 2 | 0 - learning python 5 - group meetings, online meeting 6 - learn django | 2 |  |  |  |  | 2 | 2 | 0 - learning python, git, django 4 - test exising code and softwate 5 - group meetings 6 - unit test
week 4 (02/17 - 02/24/16 | 20 | 18 | 2 | 0 - learning existing code, python 5 - group meetings, online meeting 4 - unit and ui test | 8 | 0 | 0 | 0 | 10 | 2 | 2 | 0 - learning python, git, django 4 - test exising code and softwate 5 - group meetings 6 - unit test
week 5(02/24-03/01) | 6 | 4 | 2 | 5 - group meetings, online meeting 4 - unit and ui test | 0 | 0 | 0 | 0 | 4 | 2 |  | 0
week 6(03/02 - 03/07) | 0 | 0 | 0 | 0 - learning python 5 - group meetings, online meeting 6 - search about coding standards, tools, configuration management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0-learning
week7(03/08-03/13)) | 10 | 8 | 2 | 0-learning | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 - user story implementation 4 -configuration, merging 5 - group meetings 6 - unit test
week 8(03/14 - 03/22) | 15 | 13 | 2 | 5 - group meetings, online meeting 3 - implementation, git configuration managment | 0 | 0 | 0 | 15 |  | 2 | 10 | 3 - user story implementation 4 -configuration, merging 5 - group meetings 6 - unit test
week 9(03/23 - 03/29) | 30 | 26 | 2 | Task Breakdown 0 - learning 3 - implementation 4 - test 6 - configuration, merging of changes, git fixing conflicts | 2 | 0 | 0 | 10 | 6 |  | 10 | 0 - learning 3 - implementation 4 - test 6 - unclassified
week 10(03/30-03/06) | 10 | 8 | 2 | Task Breakdown 0 - learning 3 - implementation 6- user story idea | 3 | 0 | 0 | 0 | 0 | 0 | 7 | 3-implementation
week 11(03/07-03/13) | 17 | 15 | 2 | Task Breakdown 0 - learning 3 - implementation 4 - test 6 - configuration, merging of changes, git fixing conflicts | 0 | 0 | 0 | 10 | 5 | 2 |  | 0 - learning 3 - implementation 4 - test 6 - unclassified, code coverage, statistical analysis
week12(14/07-20/07) | 30 | 28 | 2 | Task Breakdown 0 - learning 3 - implementation 4 - test 6 - configuration, merging of changes, git fixing, static code analysis | 0 | 0 | 0 | 15 | 0 | 2 | 11 | 0 - learning 3 - implementation 4 - test 6 - jenkins, code coverage, statistical analysis
week 13(21/07-27/07) | 35 | 30 | 5 | Task Breakdown 0 - learning 3 - implementation 4 - test 6 - configuration, merging of changes, git fixing, static code analysis | 4 | 0 | 0 | 0 | 10 |  | 16

## Chengchen Wang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 9 | 7 | 2 | 0 - learning Python, Django framework 1 - Doing research and viewing other similar tools, note down and analysis the features (especially TeamCity) 4 - Deploy 3BluePrints locally and configure python 5 - Group meeting 6 - Woring on the existing 3BluePrints tool & redesign meeting minutes form | 3 | 1 |  |  | 1 | 2 | 2 | 0 - Continue to learn Python, Django framework 1 - Doing research aon other other similar tools, note down and analysis the features, thinking about user stories. 5 - Group meeting 6 - Woring on the existing 3BluePrints tool & redesign meeting minutes form. | 10
week 2 (02/03 - 02/09) | 9 | 8 | 1 | 0 - Continue to learn Python, Django framework, and chart tools (Highcharts) 1 - Doing research aon other other similar tools, note down and analysis the features, thinking about user stories. And Writting SPPP Related Works Part. 4 - Testing the compatiability of Python+MySQL 5 - On class meeting and review meeting records of the missed meeting 6 - Woring on the existing 3BluePrints tool & redesign meeting minutes form. | 3 | 2 |  |  | 2 | 1 | 1 | 0 - Continue to learn Python, Django framework, and chart tools (D3.js) 1 - Doing research aon other other similar tools, note down and analysis the features, writting down user stories. 2 - Designing database tables 4 - Testing MySQL 5 - Group meeting 6 - Woring on the existing 3BluePrints tool & redesign meeting minutes form. | 20
week 3 (02/10 - 02/16) | 21 | 19 | 2 | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- Established our team's own VMware(Ubuntu)+Django+PyCharm environment and deployed the project locally and wrote a simple instructions document file 5- Group meeting | 5 |  |  | 14 |  | 2 |  | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- Established our team's Github Repository and add collabrators 5- Group meeting | 14
week 4 (02/17 - 02/23) | 13 | 11 | 2 | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- leaned and established our team's Github Repository and add collabrators 4 - designed and ran tests on test_api 5- Group meeting | 3 |  |  | 5 | 3 |  |  | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- leaned and established our team's Github Repository and add collabrators 5- Group meeting 6- Setting up MySQL+Python+Django Prequisites | 12
week 5 (02/24 - 03/01) | 12 | 10 | 2 | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- leaned and established our team's Github Repository and add collabrators 5- Group meeting 6- Setting up MySQL+Python+Django Prequisites | 3 |  |  | 1 |  | 2 | 6 | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- Implement MySQL+Python+Django 5- Group meeting | 12
week 8 (03/16 - 03/22) | 13 | 13 | 0 | 0- kearning Python, Django Framework, JavaScript(React/D3.js/HighCharts) 3- Implement MySQL+Python+Django | 5 |  |  | 8 |  |  |  | 0 - learning django 2 - design new features 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code, prepare for the presentation | 12
week 9 (03/23 - 03/29) | 11 | 9 | 2 | 0 - learning django, selenium 2 - design new features 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code, prepare for the presentation | 2 |  | 2 | 2 | 2 | 2 | 1 | 0 - learning django 2 - design new features 3 - implementation (code, ui) & modify the previous test cases 4 - test the new feature 5 - group meetings 6 - read the existing code | 12
week 10 (03/30 - 04/05) | 12 | 12 | 0 | 0 - learning django, selenium 2 - design new features 3 - implementation (code, ui) & modify the previous test cases 4 - test the new feature 5 - group meetings 6 - read the existing code | 2 |  | 1 | 7 | 1 |  | 1 | 0 - learning Ajax, HTML, JavaScript, reportLAB, XML 2 - design new features: download PDF report 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code | 12
week 11 (04/06 - 04/12) | 21 | 18 | 3 | 0 - learning Ajax, HTML, JavaScript, reportLAB, XML 2 - design new features: download PDF report 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - read the existing code | 6 |  | 3 | 7 | 1 | 3 | 1 | 2 - design new features: download PDF report 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin | 12
week 12 (04/13 - 04/19) | 20 | 20 | 0 | 2 - design new features: download PDF report 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin |  |  | 5 | 10 | 3 | 0 | 2 | 2 - design new features: sign in security issue 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin | 12
week 13 (04/20 - 04/27) | 30 | 27 | 3 | 3 - implementation (code, ui, database), Final Merge 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin, write SPPP,SDD,Test |  |  | 0 | 18 | 6 | 3 | 3

## Ruirong Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 10 | 8 | 2 | 0 - learn python 1 - get to know Project Management Tools 5 - group meetings | 6 | 2 |  |  |  | 2 |  | 0 - learn python, git 1 - try 3blueprints 5 - group meetings | 10
week 2 (02/03 - 02/09) | 9 | 7 | 2 | 0 - learn python 1 - write SPPP part 6, try 3blueprints online, use pivot tracker create new user story 5 - group meetings, online meeting | 3 | 4 |  |  |  | 2 | 2 | 0 - learn git 1 - install Virtual Machine and config the enviornment 4 - test locally 5 - group meetings | 8
week 3 (02/10 - 02/17) | 7 | 5 | 2 | 1 - install VMWare, import VM file, try run 3blueprints locally, config spf13vim in VM 4 - try use 3blueprints locally 5 - group meeting |  | 4 |  |  | 1 | 2 |  | 0 - learn Django framwork 5 - group meeting | 8
week 4 (02/18 - 02/23) | 10 | 8 | 2 | 0- kearning Python, Django Framework 3 - designed and ran tests on test_api, refactoring test_iteration 5- Group meeting | 3 |  |  | 5 |  | 2 |  | 4- complete the task in iteration I 5- group meeting 6 - complete file | 8
week 5 (02/23 - 03/01) | 9 | 7 | 2 | 0- learning Python, Django Framework, Unit test 4- design test and refactoring 5- Group meeting 6- complete SPPP file | 1 |  |  |  | 5 | 2 | 1 | 0-learning python and django 2-decide task in for iteration II 5-group meeting | 6
week 6 (03/02 - 03/09) | 8 | 6 | 2 | 0- learning Python,Django 1- write user story for iteration II 3 - working on Mysql database 5 - group meeting and sub group meeting | 2 | 1 |  | 3 |  | 2 |  | 0-learning python and django 3-start design and coding about such user story 5-group meeting | 8
week 7 (03/10 - 03/16) | 11 | 9 | 2 | 0-learning django and Mysql 3- modify the current code to work withe MySQL 4-run test under the Mysql database 5-group meeting | 3 |  |  | 4 | 2 | 2 |  | 0-learning python and Django 1-work on a new feature 3-implement the database immigration 4-run test 5-group meeting | 15
week 8 (03/17 - 03/23) | 14 | 10 | 4 | 0-learning django and python 1- write a new user story (generate project report) 2- design the new feature 3- implement the database immigration 4-run current test and create new test for the new feature 5-group meeting | 3 | 1 | 3 |  | 3 | 4 |  | 0 - learning python,django 3 - implementation 4 - test the new feature 5 - group meetings 6 - prepare for the iteration II presentation | 16
week 9 (03/24 - 03/30) | 20 | 16 | 4 | 0 - learning python,django 2 - desing generate report 3 - implement the function and the UI(generate in txt) 4 - test the new feature 5 - group meetings 6 - prepare for the iteration II presentation | 3 |  | 2 | 8 | 2 | 4 | 1 | 0-learning python and django techinics about the report and selenium 3-optimize the new feature 4-test the new feature 5-group meeting | 10
week 10 (03/31 - 04/06) | 17 | 13 | 4 | 0 - learning python,django ,reportLAB, XML,learning the current form window code 2 - design the new feature of generating report (on format and content) 3 - implement the function and the UI 4 - test the new feature 5 - group meetings | 3 |  | 2 | 6 | 2 | 4 |  | 0-learning python, Django,techinics about the report and selenium 2-design the new feature 3-implement the new feature 4-test the new feature 5-group meeting | 18
week 11 (04/7 - 04/13) | 21 | 17 | 4 | 0 - learning reportLAB, XML,learning the current form window code 2 - design for generate report, download PDF report 3 - using Ajax, JavaScprit to implementation form window and implement other function (code, ui) 4 - test the new feature 5 - group meetings | 3 |  | 2 | 10 | 2 | 4 |  | 3-complete and optimize the code 4 - test new feature 5-group meeting 6 - prepare for presentation | 25
week 12 (04/14 - 04/20) | 25 | 21 | 4 | 2 - design for generate report, download PDF report 3 - implementation (code, ui) 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin and work on SDD file |  |  | 2 | 15 | 2 | 4 | 2 | 3-complete and optimize the code 4 - test new feature 5-group meeting 6 - prepare for presentation | 25
week 13 (04/21 - 04/27) | 26 | 22 | 4 | 2-design the model of generate report in pdf and add statics analysis in the report 3 - implementation (code, ui, database), work on group merge 4 - test the new feature 5 - group meetings 6 - prepare for presentatoin, write SPPP,SDD,Test file |  |  | 1 | 17 | 2 | 4 | 2

## Deemah AlEyoni
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
week 1 (01/27 - 02/02) | 10 | 10 | 2 | 0 - start learning python & git. Installation of the PM tool locally 1 - work on other managment tools for comparison. Write Requirment analysis help docuemnt for the team. Brian storm features with team mates. 5 - Attend firt group meeting. Sign up or Slack. 4 - test and work on the PM tool to find areas of improvemnt. | 6 | 2 | 0 | 0 | 2 | 2 | 0 | 0 - continue learning python, django, git. 1 - write the requirment analysis part in SPPP document 4- Write test case secnarios for the existing system. | 10